## Sheet1
Task Name | Notes | Duration (man day) | Start | Finish | % Complete
Create Document Management | - Create site name "Document Management" + Setting privacy (only owner and member can access site) + Create document libary name "Document lab" + Create document libary name "Policies" + Create document libary name "Procedures" + Create document libary name "Forms" | 0.5 | 2022-12-07 | 2022-12-07
Create Document Center | - create site name "Document Center" + Setting privacy (anyone can access site) + Create document libary name "Document list" | 0.5 | 2022-12-07 | 2022-12-07
Document uploading flow | + Create a new flow name upload file (auto-trigger when a submitted file in "Document lab") + Add Metadata variable for file type (Procedures, Policies, Forms,...), owner email,... | 1 | 2022-12-08 | 2022-12-08
Metadata | Research about Metadata | 0.5 | 2022-12-09 | 2022-12-09
Approval/rejection flow | + Create approval and send to owner's email + owner can approve or reject the document and add comments + if the owner rejected then change the document status to "rejected", the author receives a rejection email with comments, and the document is back to the Document lab. + if the owner approved then change the document status to "approved", an author receives an acceptance email with comments, Document move to "Policies"/"Procedures"/"Forms" and appears in "Document Center" | 1.5 | 2022-12-09 | 2022-12-11